## Trang tính1
AI and smart vision for house management
WBS | Name | PIC | Estimated Time | Start Date | Due Date | Dependencies | Week 4 (27 May - 31 May) |  |  |  |  | Week 5 (3 June - 7 June) |  |  |  |  | Week 6 (10 June - 14 June) |  |  |  |  | Week 7 (17 June - 21 June) |  |  |  |  | Week 8 (24 June - 28 June) |  |  |  |  | Week 9 (8 July - 12 July) |  |  |  |  | Week 10 (15 July - 19 July) |  |  |  |  | Week 11 (22 July - 26 July)
[7 empty] | 2 | 3 | 4 | 5 | 6 | 2 | 3 | 4 | 5 | 6 | 2 | 3 | 4 | 5 | 6 | 2 | 3 | 4 | 5 | 6 | 2 | 3 | 4 | 5 | 6 | 2 | 3 | 4 | 5 | 6 | 2 | 3 | 4 | 5 | 6 | 2 | 3 | 4 | 5 | 6
1 | Project Planning |  | ~5 days | 27 May | 31 May | bar: Week 4 (27 May - 31 May) 2 to Week 4 (27 May - 31 May) 6
2024-01-01 | Define project background, issues, requirements | Dat | ~1 day | bar: Week 4 (27 May - 31 May) 2
2024-02-01 | Define project objectives, deliverables, and scope | Duc Anh, Vu | ~2 days | bar: Week 4 (27 May - 31 May) 3 to Week 4 (27 May - 31 May) 4
2024-03-01 | Identify project risks and mitigation plans | Nam | ~1 day | bar: Week 4 (27 May - 31 May) 4
2024-04-01 | Develop project timeline and milestones | Nghia | ~1 day | bar: Week 4 (27 May - 31 May) 4
2024-05-01 | Adjust and Finalise project plan | All Members | ~2 days |  |  | 1.1, 1.2, 1.3, 1.4 | bar: Week 4 (27 May - 31 May) 4 to Week 4 (27 May - 31 May) 5
2024-06-01 | Obtain approval for project planning | All Members | ~1 day |  |  | 2024-05-01 | bar: Week 4 (27 May - 31 May) 6
2 | User Interface (UI) Design |  | ~5 days | bar: Week 5 (3 June - 7 June) 2 to Week 5 (3 June - 7 June) 6
2024-01-02 | Develop wireframes and design prototypes | All Members | ~1 day |  |  | 2024-06-01 | bar: Week 5 (3 June - 7 June) 2
2024-02-02 | Review and approve wireframes with stakeholders | Dat | ~1 day |  |  | 2024-01-02 | bar: Week 5 (3 June - 7 June) 3
2024-03-02 | Develop high-fidelity UI designs | Duc Anh, Vu, Nam | ~2 days |  |  | 2024-02-02 | bar: Week 5 (3 June - 7 June) 4 to Week 5 (3 June - 7 June) 5
2024-04-02 | Conduct usability testing and gather feedback | Nghia, Duc Anh | ~1 day |  |  | 2024-03-02 | bar: Week 5 (3 June - 7 June) 6
2024-05-02 | Finalize UI designs | All Members | ~1 day |  |  | 2024-04-02 | bar: Week 5 (3 June - 7 June) 6
3 | Web Application Development |  | ~14 days | bar: Week 6 (10 June - 14 June) 2 to Week 8 (24 June - 28 June) 5
2024-01-03 | Design database schema | All Members | ~2 days |  |  | 2024-05-01 | bar: Week 6 (10 June - 14 June) 2 to Week 6 (10 June - 14 June) 3
2024-02-03 | Implement database | Duc Anh, Vu, Nam | ~2 days |  |  | 2024-01-03 | bar: Week 6 (10 June - 14 June) 4 to Week 6 (10 June - 14 June) 5
2024-03-03 | Develop backend services | Duc Anh, Vu, Nam | ~7 days |  |  | 2024-02-03 | bar: Week 6 (10 June - 14 June) 5 to Week 7 (17 June - 21 June) 6
2024-04-03 | Develop frontend components | Duc Anh, Vu, Nam | ~7 days |  |  | 2024-05-02 | bar: Week 6 (10 June - 14 June) 5 to Week 7 (17 June - 21 June) 6
2024-05-03 | Integrate backend with frontend | Duc Anh, Vu, Nam | ~3 days |  |  | 3.3, 3.4 | bar: Week 7 (17 June - 21 June) 6 to Week 8 (24 June - 28 June) 2
2024-06-03 | Test and Fix bugs | Duc Anh, Vu, Nam | ~5 days |  |  | 2024-05-03 | bar: Week 8 (24 June - 28 June) 2 to Week 8 (24 June - 28 June) 4
2024-07-03 | Document the system architecture | Duc Anh, Vu, Nam | ~2 days |  |  | 2024-06-03 | bar: Week 8 (24 June - 28 June) 4 to Week 8 (24 June - 28 June) 5
4 | Data Collecting and Processing |  | ~8 days | bar: Week 6 (10 June - 14 June) 2 to Week 7 (17 June - 21 June) 4
2024-01-04 | Search and Collect suitable satellite image dataset | Dat, Nghia | ~4 days |  |  | 2024-05-01 | bar: Week 6 (10 June - 14 June) 2 to Week 6 (10 June - 14 June) 5
2024-02-04 | Perform data annotation with the dataset | Dat, Nghia | ~2 days |  |  | 2024-01-04 | bar: Week 6 (10 June - 14 June) 5 to Week 6 (10 June - 14 June) 6
2024-03-04 | Perform data augmentation with the dataset | Dat, Nghia | ~2 days |  |  | 2024-02-04 | bar: Week 6 (10 June - 14 June) 6 to Week 7 (17 June - 21 June) 2
2024-04-04 | Conduct data preprocessing and split to train/test set | Dat, Nghia | ~2 days |  |  | 2024-03-04 | bar: Week 7 (17 June - 21 June) 3 to Week 7 (17 June - 21 June) 4
2024-05-04 | Store preprocessed images in database | Dat, Nghia | ~1 day |  |  | 3.1, 4.3 | bar: Week 7 (17 June - 21 June) 5
5 | Computer Vision and AI Model Development |  | ~10 days | bar: Week 7 (17 June - 21 June) 2 to Week 8 (24 June - 28 June) 6
2024-01-05 | Research and Choose the suitable model architecture | Dat, Nghia | ~3 days |  |  | 2024-05-01 | bar: Week 7 (17 June - 21 June) 2 to Week 7 (17 June - 21 June) 4
2024-02-05 | Set up the training environment | Dat, Nghia | ~2 days |  |  | 2024-01-05 | bar: Week 7 (17 June - 21 June) 4 to Week 7 (17 June - 21 June) 5
2024-03-05 | Train the model using the training dataset | Dat, Nghia | ~3 days |  |  | 5.2, 4.5 | bar: Week 7 (17 June - 21 June) 6 to Week 8 (24 June - 28 June) 3
2024-04-05 | Evaluate the model on the test set using various metrics | Dat, Nghia | ~4 days |  |  | 2024-03-05 | bar: Week 8 (24 June - 28 June) 2 to Week 8 (24 June - 28 June) 5
2024-05-05 | Perform cross-validation to ensure robustness | Dat, Nghia | ~2 days |  |  | 2024-04-05 | bar: Week 8 (24 June - 28 June) 5 to Week 8 (24 June - 28 June) 6
6 | Model Deployment and Integration |  | ~5 days | bar: Week 9 (8 July - 12 July) 2 to Week 9 (8 July - 12 July) 6
2024-01-06 | Deploy the trained model to cloud platform | Dat, Vu | ~4 days |  |  | 2024-05-05 | bar: Week 9 (8 July - 12 July) 2 to Week 9 (8 July - 12 July) 3
2024-02-06 | Develop APIs and integrate into the web application | All Members | ~4 days |  |  | 2024-01-06 | bar: Week 9 (8 July - 12 July) 4
2024-03-06 | Perform user acceptance testing (UAT) with stakeholders | Dat | ~4 days |  |  | 2024-02-06 | bar: Week 9 (8 July - 12 July) 5 to Week 9 (8 July - 12 July) 6
7 | Project Document |  | ~5 days | bar: Week 10 (15 July - 19 July) 2 to Week 10 (15 July - 19 July) 6
2024-01-07 | Conduct project review meeting | All Members | ~ 3 days |  |  | 3.7, 6.2 | bar: Week 10 (15 July - 19 July) 2
2024-02-07 | Finalize document system architecture and code | All Members | ~ 3 days |  |  | 3.7, 6.2 | bar: Week 10 (15 July - 19 July) 3 to Week 10 (15 July - 19 July) 4
2024-03-07 | Obtain formal project acceptance from stakeholders | All Members | ~ 3 days |  |  | 2024-01-07 | bar: Week 10 (15 July - 19 July) 5
2024-04-07 | Monitoring and Support | All Members |  |  |  | 2024-02-07 | bar: Week 10 (15 July - 19 July) 6
Gray task for both teams
Blue tasks for SE team
Green tasks for DS-AI team
Project Manager: Thanh Dat Nguyen Company Name: NTT e-MOI
Project Team: Group 2 IT Project Date: 2 June 2024